## Jira Import
Summary | Issue Type | Description | Epic Name | Sprint | Priority | Story Points | Component | Labels | Layer | Acceptance Criteria
Platform Foundation | Epic | Admin auth, integration settings singleton, audit logging, API documentation. |  | Sprint 1 | High |  | Backend | foundation | Backend
Stripe Payments | Epic | Stripe PaymentIntent/Checkout Session, webhooks, checkout payment_method branching. |  | Sprint 1 | Highest |  | Backend | stripe | Backend
Admin Interface | Epic | React admin app: dashboard, settings, operations screens. |  | Sprint 1-4 | High |  | Admin | admin | Admin
Courier Integrations | Epic | TCS and Leopard adapters, shipment booking, label generation. |  | Sprint 2 | Highest |  | Backend | courier | Backend
Tracking Module | Epic | Carrier status polling, webhooks, unified tracking dashboard. |  | Sprint 2-4 | High |  | Backend | tracking | Backend
Email Notifications | Epic | Transactional email provider, templates, triggers. |  | Sprint 3 | High |  | Backend | email | Backend
Invoice Generation | Epic | PDF invoices for orders, storage, email attachment. |  | Sprint 3 | High |  | Backend | invoice | Backend
Import Export | Epic | Bulk catalog import/export via async jobs. |  | Sprint 3 | High |  | Backend | import-export | Backend
Store Locator | Epic | Physical store locations, geo search, pickup. |  | Sprint 4 | Medium |  | Backend | stores | Backend
AI Assistant | Epic | Product/collection search chatbot with tool calling. |  | Sprint 4 | High |  | Backend | ai | Backend
POS Module | Epic | In-store POS sessions, sales, receipts. |  | Sprint 4 | High |  | Backend | pos | Backend
Staff roles and admin JWT/session auth | Task | Implement IsAdminUser or custom Role model; protect /admin/* API routes. | Platform Foundation | Sprint 1 | High | 5 | Backend | auth,admin | Backend | Non-staff users receive 403 on admin endpoints.
IntegrationSettings encrypted singleton model | Task | Store Stripe, email, TCS, Leopard, AI credentials encrypted at rest. | Platform Foundation | Sprint 1 | High | 5 | Backend | settings,integrations | Backend | Settings CRUD via admin API; secrets masked in responses.
Stripe PaymentIntent or Checkout Session on checkout | Task | Tie Stripe payment to checkout_id; return client_secret or checkout_url for card flow. | Stripe Payments | Sprint 1 | Highest | 8 | Backend | stripe,payments | Backend | Card checkout initiates Stripe without completing order until paid.
Stripe webhook payment_intent.succeeded | Task | Webhook sets order financial_status=paid; idempotency keys for retries. | Stripe Payments | Sprint 1 | Highest | 8 | Backend | stripe,webhooks | Backend | Duplicate webhook events do not corrupt order state.
Extend checkout complete for payment_method cod¦card | Task | POST /checkouts/{id}/complete/ branches: COD completes immediately; card returns payment payload. | Stripe Payments | Sprint 1 | High | 5 | Backend | checkout,api | Backend | API accepts payment_method and returns correct response per method.
POST /checkouts/{id}/payment/ endpoint | Task | Initiate or confirm Stripe payment; return client_secret or checkout_url. | Stripe Payments | Sprint 1 | High | 5 | Backend | stripe,api | Backend | Documented in OpenAPI; works with storefront card flow.
Admin audit log for integration changes | Task | Log admin actions on settings and sensitive operations. | Platform Foundation | Sprint 1 | Medium | 3 | Backend | audit,admin | Backend | Audit entries show actor, action, timestamp.
OpenAPI: document Sprint 1 payment endpoints | Task | Update drf-spectacular for payment and webhook routes. | Platform Foundation | Sprint 1 | Medium | 2 | Backend | docs,api | Backend | Endpoints visible in /api/docs/.
Storefront: send payment_method on checkout complete | Task | Wire paymentMethod into finalizePayload in Checkout.tsx. | Stripe Payments | Sprint 1 | High | 3 | Storefront | stripe,checkout | Storefront | Selected COD or card is sent to API on submit.
Storefront: Stripe redirect/confirm return flow | Task | Handle Stripe return URL and payment confirmation after redirect. | Stripe Payments | Sprint 1 | High | 5 | Storefront | stripe,checkout | Storefront | Successful card payment lands on order confirmation page.
Storefront: VITE_STRIPE_PUBLISHABLE_KEY env config | Task | Document and type Stripe publishable key in .env.example. | Stripe Payments | Sprint 1 | Low | 1 | Storefront | stripe,config | Storefront | Env var documented for production builds.
Admin app bootstrap: login and dashboard shell | Story | New admin-ui routes: staff login, layout, navigation. | Admin Interface | Sprint 1 | High | 8 | Admin | admin,ui | Admin | Staff can log in and access dashboard shell.
Admin Integration Settings page | Story | UI to read/write masked Stripe, courier, email, AI credentials. | Admin Interface | Sprint 1 | High | 5 | Admin | admin,settings | Admin | Integration keys editable without exposing full secrets.
CourierAdapter abstract interface | Task | Methods: create_shipment, get_label, track, cancel. | Courier Integrations | Sprint 2 | High | 5 | Backend | courier,architecture | Backend | Adapters pluggable by carrier code.
TCS courier adapter (sandbox) | Story | TCS API for booking, labels, tracking in sandbox. | Courier Integrations | Sprint 2 | Highest | 13 | Backend | tcs,courier | Backend | Test AWB created; tracking returns status.
Leopard courier adapter (sandbox) | Story | Leopard API for booking, labels, tracking in sandbox. | Courier Integrations | Sprint 2 | Highest | 13 | Backend | leopard,courier | Backend | Test AWB created; tracking returns status.
POST /orders/{id}/fulfillments/ API | Task | Create fulfillment with carrier; auto-book or manual AWB. | Courier Integrations | Sprint 2 | High | 8 | Backend | fulfillment,api | Backend | Fulfillment saved with tracking_number and service FK.
GET /tracking/{awb}/ public tracking lookup | Task | Resolve AWB to carrier status for admin and customers. | Tracking Module | Sprint 2 | Medium | 5 | Backend | tracking,api | Backend | Returns latest scan events for valid AWB.
Celery beat: poll carrier tracking status | Task | Update Fulfillment.status from TCS/Leopard APIs. | Tracking Module | Sprint 2 | High | 8 | Backend | celery,tracking | Backend | Statuses sync to in_transit/success automatically.
Carrier webhook endpoints (if supported) | Task | Push updates from TCS/Leopard when available. | Courier Integrations | Sprint 2 | Medium | 5 | Backend | webhooks,courier | Backend | Webhook updates fulfillment near real-time.
Admin fulfillment queue UI | Story | Filter by status, carrier, date; action unfulfilled orders. | Admin Interface | Sprint 2 | High | 8 | Admin | admin,fulfillment | Admin | Staff can create fulfillments from queue.
Admin bulk print shipping labels | Task | Download/print labels for selected fulfillments. | Courier Integrations | Sprint 2 | Medium | 5 | Admin | admin,labels | Admin | Bulk label download works for TCS and Leopard.
Admin courier config per FulfillmentService | Task | Link carrier credentials to fulfillment service profiles. | Courier Integrations | Sprint 2 | Medium | 3 | Admin | admin,courier | Admin | Each service uses correct carrier account.
Storefront: optional fulfillment status_detail badge | Task | Show carrier scan message on OrderDetail when API provides status_detail. | Tracking Module | Sprint 2 | Low | 2 | Storefront | tracking,orders | Storefront | Latest carrier message visible on order page.
OpenAPI: document fulfillment and tracking endpoints | Task | Schema for Sprint 2 APIs. | Courier Integrations | Sprint 2 | Low | 2 | Backend | docs,api | Backend | Swagger updated.
Email provider abstraction (SendGrid/Resend/SMTP) | Task | Pluggable backend with Django HTML templates. | Email Notifications | Sprint 3 | High | 5 | Backend | email,integrations | Backend | Test email sends via configured provider.
Email trigger: order confirmation | Task | Send on order complete with line items summary. | Email Notifications | Sprint 3 | High | 3 | Backend | email,orders | Backend | Customer receives confirmation after purchase.
Email trigger: payment receipt | Task | Send when financial_status becomes paid. | Email Notifications | Sprint 3 | Medium | 2 | Backend | email,payments | Backend | Receipt email sent for card payments.
Email trigger: shipped with tracking link | Task | Send when fulfillment ships. | Email Notifications | Sprint 3 | High | 3 | Backend | email,shipping | Backend | Email contains working track URL.
Email trigger: password reset | Task | Wire auth reset flow to email provider. | Email Notifications | Sprint 3 | Medium | 2 | Backend | email,auth | Backend | Reset link delivered via email.
POST /orders/{id}/resend-confirmation/ admin endpoint | Task | Staff can resend order confirmation email. | Email Notifications | Sprint 3 | Low | 2 | Backend | email,admin | Backend | Resend rate-limited and logged.
PDF invoice generator | Story | WeasyPrint/reportlab: lines, tax, shipping, company header. | Invoice Generation | Sprint 3 | High | 8 | Backend | invoice,pdf | Backend | PDF matches order totals.
GET /orders/{id}/invoice.pdf endpoint | Task | Auth: customer owns order or staff. | Invoice Generation | Sprint 3 | High | 3 | Backend | invoice,api | Backend | Authorized download; others 403.
Store invoice PDF in Cloudinary/S3 | Task | Persist PDF; attach URL to confirmation email. | Invoice Generation | Sprint 3 | Medium | 3 | Backend | invoice,storage | Backend | PDF URL stored on order record.
Admin invoice download on order detail | Task | Download button in admin order view. | Invoice Generation | Sprint 3 | Medium | 2 | Admin | admin,invoice | Admin | Staff downloads invoice from order.
Storefront invoice download on order detail | Task | Customer download link on OrderDetail page. | Invoice Generation | Sprint 3 | Medium | 2 | Storefront | invoice,orders | Storefront | Customer downloads own invoice PDF.
Celery import job: products variants collections inventory | Story | CSV/XLSX validate, preview, commit; error report. | Import Export | Sprint 3 | High | 13 | Backend | import,celery | Backend | 100+ rows import async without blocking.
Celery export job with catalog filters | Task | Export matches list API filters. | Import Export | Sprint 3 | Medium | 5 | Backend | export,celery | Backend | Filtered XLSX/CSV download.
POST /admin/import/{entity}/ and GET /admin/export/{entity}/ | Task | Admin APIs for import/export jobs. | Import Export | Sprint 3 | High | 5 | Backend | import-export,api | Backend | Job status polling endpoint documented.
Admin import wizard UI | Story | Upload, preview, run, download errors. | Import Export | Sprint 3 | High | 8 | Admin | admin,import | Admin | Staff completes import with progress feedback.
Admin export with filters UI | Task | Export from catalog admin views. | Import Export | Sprint 3 | Medium | 3 | Admin | admin,export | Admin | Export respects current filters.
Admin email template editor | Story | Edit subject/body with variable documentation. | Email Notifications | Sprint 3 | Medium | 5 | Admin | admin,email | Admin | Templates saved and used by triggers.
StoreLocation model and migrations | Task | Fields: name, lat, lng, address, hours, phone, is_pickup_enabled. | Store Locator | Sprint 4 | High | 3 | Backend | stores,models | Backend | CRUD via admin API.
GET /stores/ with geo query | Task | ?lat=&lng=&radius_km= returns nearest stores. | Store Locator | Sprint 4 | High | 5 | Backend | stores,api | Backend | Geo search returns sorted results.
Admin store CRUD with map pin picker | Story | Manage locations on interactive map. | Store Locator | Sprint 4 | High | 8 | Admin | admin,stores | Admin | Staff adds/edits stores with map UI.
Storefront store locator page | Story | Map/list; find nearest store by location. | Store Locator | Sprint 4 | High | 8 | Storefront | stores,locator | Storefront | Customers find stores on /stores page.
PDP optional pick up at store | Task | Pickup store selection when API supports. | Store Locator | Sprint 4 | Low | 5 | Storefront | stores,pickup | Storefront | Pickup store selectable at checkout when enabled.
Catalog embeddings index for AI search | Task | Sync products/collections to embeddings table. | AI Assistant | Sprint 4 | High | 8 | Backend | ai,search | Backend | Index refreshes on catalog changes.
POST /assistant/chat with tool calling | Story | Tools: search_products, search_collections, get_product. | AI Assistant | Sprint 4 | High | 13 | Backend | ai,api | Backend | Natural language returns relevant products.
AI rate limits and prompt guardrails | Task | Token caps; no PII in logs. | AI Assistant | Sprint 4 | Medium | 3 | Backend | ai,security | Backend | Abuse limited; logs sanitized.
Admin AI prompt and logs config | Task | Configure system prompt; view sanitized logs. | AI Assistant | Sprint 4 | Medium | 5 | Admin | admin,ai | Admin | Staff adjusts assistant from admin.
Storefront AI chat widget | Story | Floating widget on home, PLP, PDP. | AI Assistant | Sprint 4 | High | 8 | Storefront | ai,chat | Storefront | Users search products via chat.
POS models: Register PosSession PosSale | Task | Link PosSale to Order; session open/close. | POS Module | Sprint 4 | High | 5 | Backend | pos,models | Backend | Models migrated and in admin API.
POS APIs: sessions and sales | Story | Open/close session, cart, cash/card split, receipt payload. | POS Module | Sprint 4 | High | 13 | Backend | pos,api | Backend | Complete sale creates order.
Inventory decrement on POS/order complete | Task | Stock decreases on successful sale. | POS Module | Sprint 4 | Medium | 5 | Backend | pos,inventory | Backend | Inventory accurate after POS sale.
Admin POS UI: barcode scan and quick search | Story | In-store POS screen for cashiers. | POS Module | Sprint 4 | High | 13 | Admin | pos,ui | Admin | Cashier completes sale from POS UI.
Unified admin tracking dashboard | Story | Orders to fulfillments to carrier timeline; filters; CSV export. | Tracking Module | Sprint 4 | High | 13 | Admin | admin,tracking | Admin | Delayed/exception orders visible; CSV export works.
OpenAPI: document Sprint 4 endpoints | Task | stores, assistant, pos in schema. | Platform Foundation | Sprint 4 | Low | 2 | Backend | docs,api | Backend | Swagger complete for Sprint 4.

## Epics Only
Summary | Issue Type | Description | Epic Name | Sprint | Priority | Story Points | Component | Labels | Layer | Acceptance Criteria
Platform Foundation | Epic | Admin auth, integration settings singleton, audit logging, API documentation. |  | Sprint 1 | High |  | Backend | foundation | Backend
Stripe Payments | Epic | Stripe PaymentIntent/Checkout Session, webhooks, checkout payment_method branching. |  | Sprint 1 | Highest |  | Backend | stripe | Backend
Admin Interface | Epic | React admin app: dashboard, settings, operations screens. |  | Sprint 1-4 | High |  | Admin | admin | Admin
Courier Integrations | Epic | TCS and Leopard adapters, shipment booking, label generation. |  | Sprint 2 | Highest |  | Backend | courier | Backend
Tracking Module | Epic | Carrier status polling, webhooks, unified tracking dashboard. |  | Sprint 2-4 | High |  | Backend | tracking | Backend
Email Notifications | Epic | Transactional email provider, templates, triggers. |  | Sprint 3 | High |  | Backend | email | Backend
Invoice Generation | Epic | PDF invoices for orders, storage, email attachment. |  | Sprint 3 | High |  | Backend | invoice | Backend
Import Export | Epic | Bulk catalog import/export via async jobs. |  | Sprint 3 | High |  | Backend | import-export | Backend
Store Locator | Epic | Physical store locations, geo search, pickup. |  | Sprint 4 | Medium |  | Backend | stores | Backend
AI Assistant | Epic | Product/collection search chatbot with tool calling. |  | Sprint 4 | High |  | Backend | ai | Backend
POS Module | Epic | In-store POS sessions, sales, receipts. |  | Sprint 4 | High |  | Backend | pos | Backend

## Sprint Summary
Sprint | Weeks | Goal | Tasks | Story Points
Sprint 1 | 1-2 | Platform foundation and Stripe payments | 13 | 63
Sprint 2 | 3-4 | TCS/Leopard couriers and tracking | 12 | 77
Sprint 3 | 5-6 | Email, invoices, import/export | 17 | 74
Sprint 4 | 7-8 | Store locator, AI, POS, tracking dashboard | 16 | 117
Total | 8 weeks | Ecommerce platform integrations | 58 | 331

## Import Guide
Jira import instructions
1. Create Sprints in Jira: Sprint 1, Sprint 2, Sprint 3, Sprint 4
2. Create Components: Backend, Admin, Storefront
3. Import order: Epics Only sheet first, then Jira Import sheet (tasks)
Column mapping (CSV/Excel import):
Summary -> Summary
Issue Type -> Issue Type (Epic, Story, Task)
Description -> Description
Epic Name -> Epic Link (create epics first)
Sprint -> Sprint
Priority -> Priority
Story Points -> Story point estimate
Component -> Component/s
Labels -> Labels
Layer -> Label or custom field
Acceptance Criteria -> Description footer or custom field
Note: Storefront is DONE for baseline; remaining storefront rows are thin integration only.
Backend work is in Django API (external to storefront repo).